## Sheet1
SI.NO | Subject | ASTA OWNER'S RESPONSE Dtd 23/2/2021 | CG Update as on 08/03/2021 | ASTA OWNER'S RESPONSE Dtd 14/3/2021
1 | Corpus fund | Please give more clarity about the election process and election of new members including president and others committee members .Please also explain CG role in conducting election and handing over to the elected association as we already have an association formed. Corpus fund will be available to the elected association 45days from 1st July . please confirm our understanding. | The Circular of the process has been shared to all owners dated 06/03/2021. | CGAAOA ( CASA GRAND ASTA APARTMENT OWNERS ASSOCIATION will be conducting its own elections and choosing its own Team of Office Bearers by 25th April 2021 and once the new Elected body isformed the same will be informed to CG HO
2 | Handing over to be done June 21 | As discussed the Handing over Formalities can happen from the 1st Week of June 2021 .This is clarified | This is Clarified | clarification on Handing over Agreed
3 | METROWATER ISSUE& RO plant | Water is one of the main issue prevaling in the CG asta community as we are now totally dependent on Tanker lorries as of now. We feel to have an alternative water source either from borewell /Metro water which will take care of the entire requirement of all houses in ASTA. We had a detailed discussion on 26th Jan 2020 and Mr. Bommu was supposed to test the bore well water and we also wanted CG support to issue letter to Metro water for new connection. We also spoke about studying the feasibility of putting up WTP as bore well water is not portable as per last test taken in 2019 and also we wanted to explore borewell/Well exploration in new places considering the recent rain and we wanted CG support to get this done. As a community we will also independently try with our expertise of owners in this field and submit a report shortly, Immeidate requirement is testing of exisging bore well and letter to Metro water for new connection. | Metro water has not been promised initially or any payment collected for the same from the Owners. Hence, the association or the owners to take it forward accordingly. | We strongly disagree with your reply,water is the basic amenity which is promised by CG and it is the responsibility of the builder to provide basic necessity of water .Your Reply to this is in total contradiction with our earlier discussion along with your team .This is the most important Agenda and needs to be discussed at length.An Amount of Rs 7L has been paid by all the owners towards Water/EB/Sewage/Club House.As discussed on the 30th Jan Meeting that Mr Chandra Bommu also had accepted that Initially CG had applied for Metro Water Connection and the same was not pursued further . Water team from Casa grand asta owners have confirmed with metro water department that CG has given an letter previously for metro water connection but not followed up .We had discussed about the Alternate source of Water like the Borewell which has been identified in C and D Block for again retesting. We have taken a quote from a RO plant installer and they have confirmed feasbility of converting the bore water to usable water and cost of installing will be in the range of 10-15lakhs . We look forward for CG support to work on both metro and bore well RO plant along with our water team to amicable resolve this as presently buying water from tanker will be expensive and it is CG sole responsibility to provide basic amenity.
4 | Wall Plastering | Wall plastering issue continue to be also the main issue as water . Still many owners feel that ICARE has not attended their issues and we also discussed on extension of warranty to currently from 5 years to 10 years which is not been highlighted in the reply. We request you to appoint more resources in the ASTA community to speed up the reworking and complaints .We got feedback from many that call from ICARE has not been received and reply from ICARE team is taking more than 20-30 days to resolve. New customer care number is shared with all but it is not effective . Please look in to it and speed up the process. | Work is in progress. Total units with Wall plastering issue are 12. Plastering work done for 8 Units and painting work is in progress. Plastering work for balance 4 units will be completed by this week. | This is the Second Issue in Priority.The Quality of Inner Plastering and uter Plastering has been Poor.It has been addressed on 19th Jan meeting and reply from CG was you will be collecting samples from 10 places and test the quality of the same and provide us extended warranty in writing.But there has been no communication from your side.Alreayd an Excel sheet of the Unattended complaints have been sent to the mail id of Mr Anukumar,Gavin from HO and to Icare on 10th March 2021.There are major issues of the AC Units,Curtain Rods Falling of and Peeling of the Plastering has been a major issue with 50% of the Residents.Even there is seepage and Leakage from Bathroon and ODU also which has been brought to the notice..We request a very strong and stringent action plan to address this issue like extending the warrenty period and also reimbursing the cost of plastering . We look forward for a constructive agreement between us on this issue as you have all agreed with the poor plastering done by CG .
5 | EB Connection needs to be shared by CG in 1 week | The transformers have been erection - and the EB Transfer Forms have also been sent back to CG. Awaiting for the Meters and the connection and Hope to have the EB by the 1st week of March 2021 .Please reconfirm as we cannot be dependent only on Genset as the number of people occupying the flat has increased from last discussion. This will lead to power shutdown and repair of Genset . | All Documentation and request are been processed to the EB Office. Due to the upcoming election, the Government officials are unable to be contacted. However we will ensure this process is completed at the earliest. Any maintenance towards the Genset can be looked into as we have time till June. | We request you to kindly ensure that the EB connection will be given at the earliest since the DG set is in Use 24X7 the wear and tear is very high.So Kindly follow up witb the EB for getting the connection at the earliest.Most of the owners have filled up the form also and sent to the respective CRM also
6 | STP issue | The STP is operational and we havent seen the Lorries coming into the premises for the past 2 weeks .I hope this is taken care. | This is Clarified | clarified
7 | WTP issue | We need to discuss and evaluate them for future functioning of the WTP for using bore well water. We will come back with the independent study and quote for WTP to use bore water. | WTP is Operational and only lorry water which goes to the sump is possible. Bore well connectivity to WTP has no access. | This needs more clarity ,when we discuss on placing RO plant. We can discuss on this.
8 | NOC to be done fast mode | Process Noted | This is Clarified | clarified
9 | Swimming pool issue(seating around pool) | We appreciate the Immediate Progress and would like to inform that 3 seating arrangements have been provided near the pool.This should be CG sponsored and not deducted from corpus fund. | This facility will not be deducted from the Corpus Fund. | Clarified
10 | CCTV camera to be strengthen. | More security cameras is required and also security personnel to be employed. This needs to be done before as we forsee lot of security issues prevailing in the flat. We can explain in detail over phone. | We shall look into the possibilities once the association is formed. | Clarified
11 | Association need computer | Mutually Aggreed | This is Clarified
12 | Badminton post and cricket pitch needs more light | Lightning is not sufficient and in the night we cannot play. We have put some temporary arrangement for the badmitton court and we want CG to sponsor net and other amenities for the badmitton. Pole is required to be grounded and cost should not be deducted from corpus fund. This should be CG sponsored. | As per the duly signed construction agreement Specification, we have not provided a Badminton court but a facility of abstract landscaping. Therefore converting to badminton court will not be under CG scope. | Clarified
13 | Compound wall height to be raised | This should be also addressed immediately as to protect and strengthen the secturiy of CG Asta | Work is in progress and will complete it on or before 20th of March 2021. | We need the Plastering of the Outer side of the Compound wall to be done and we have already seen that the Fencing work has been started and we request for a Barbed wire fencing which will be of more security.
14 | Garbage disposal box to be provided | Appreciate the Immediate Action taken to provide the Bins and create and healthy envirronment for Garbage Clearance | This is Clarified | Clarified
15 | Solar power solution for common areas | Will Appreciate if it can be done so that EB Bills can be saved on the common areas. This needs immediate attention. | As per the duly signed construction agreement Specification, such facility of solar power solution for common areas is not part of the project. | Clarified
16 | Intercom | Though My Gate App is there but Intercoms will be more convenient as many people are nt well cnversed with using the app . Last time it was disussed that CG will support for arrangement of Intercom as this was mentioned in the prospectus. Please clarify on the instrument purchse and the specification to clarity it to owners. Please nominate someone to take this forward. | Only the provision for intercom facility is given by CG, Instrument to be purchased by owners Asta as per CG's norms | Clarified
17 | Occupancy Certificate | please ask CRM to share it to the respective owners as we have received only the completion certificate from RERA. | We have the completed certificate of Asta, this will be shared to association once formed. | Clarified.We require the Occupation Certificate.We als request whether the Consent To Occupy ( CTO ) document has been procured from the TNPCB.If yes Kindly share the document as per the latest GO.
18 | GYM requirements(need heavier dumb bells) | A few suggestions from the Group Members.1.Weight- Kettlebell-4nos 2. Wieght Dumbell for Ladies - 6 nos . 3.Medicine Ball- 3nos wt 2kg,3kg,5kg 4.Swiss Ball - 2 Nos 5. Battle Rope - 1no 6.Hydraulic Bench Press : 1no 7.Weigh Machine- 1no 8.Music System with Speakers 9. Yoga Mats : 5nos 10. Agility Floor Ladder- I no 11. Cones 7 Nos 12 . One more thread mill is required. More requirement of tumbles The Pool Table Quality has been found to be very Poor Request the concerned team to look into the same | CG has provided the Gym equipment as per the design. Therefore for further equipment we will not be in a position to provide. | Clarified
19 | Pest Controller(powered chemical not tobe used) | Point Noted and thanks for the Information | This is Clarified | Clarified
20 | TERRACE ACCESS | As discussed in the meeting H Block is facing lot of issues in the absence of a Balcony. Kindly appreciate if H block can be provided immediate access. Majority of them participated the meeting have raised this concern and need immediate attention. Please let us know the way out through your icare coordinator. | As per CG norms, terrace access is not provided due to safety reasons. Therefore once the association is formed may take it forward. | Clarified
21 | First Aid room | It was discussed and identlfied two rooms in the parking space. Request icare coordinator to clean up the place and keep necessary first aid kits for the benefit of the owners. Apart from that for Emergencies we Require Wheel Chairs and Stretchers to be provided one for Each Block | As per the duly signed construction agreement Specification, such facility of Wheel Chair or Stretcher are not provided. However this can be taken up by the association once formed. We have already provided the first aid kit and We will inform our IFM team to have the rooms cleaned and kept. | First Aid Room has been identified We need it to be designated
22 | VISITOR PARKING FOR ASTA | This is also a major issue and a point of discussion As frequently we have observed that there is no reserve parking for the Visitor Vehicles and as per the Govt Clauses also 10% should be reserved for Visitor area Parking.Kindly address this issue also | This project doesn't have visitor's car parking due to the volume of apartments and the requirements of the car parking provided to the owners. | As per the GO 10% of the space has to be allotted for Visitors Parking Why this not been done is not known.In future the Residents will face lot of issues if not addressed as there is no provision of Parking outside the premised also because this being a Main Road Location
23 | CAR PARKING SLOTS | There are certain slots which have a narrow Parking like 180 T and the owner has addressed his issues of the Pillars being obstructing Request to address these Kind of issues. | The parking slot is provided as per the specification, Drawings and design. Therefore there is no deviation. | This issue has to be sorted out for a few Owners only We will address it separately